| Subject: ACE: kick-off meeting d.d. April 26t h & 27th 2001 |  |  |  |
| --- | --- | --- | --- |
| Prepared by: Harrie Bohnen Location: Amsterdam |  | Code-/Ordernumber: 1370000.1 |  |
| Participants: |  | Distribution: |  |
| Bohnen Buijs (gedeeltelijk) Ehlert Van den Elzen (gedeeltelijk) Hanson Kacer Knibbe Rerucha Rothkrantz Rutten (gedeeltelijk) Sletterink Van Westrenen | NLR KLu TUD KLu NLR MA TUD MA TUD NLR TUD NLR | Participants CPD, V, VE V. Rapcan (MA) |  |

The kick-off meeting of the project Adaptive Cockpit Environment (ACE), funded by the Dutch MoD and monitored by the Royal Netherlands Air Force was held at NLR on April 26th & 27th 2001.

The programme of the meeting is attached to these Minutes. For detailed information regarding project status and project co-ordination see also this attachment.

These Minutes are about the results of the discussions, decisions made and action items.

Project status

Due to the delay in contracting a new start and end date of the project is requested: January 1ste 2001 / December 31th 2003 (instead of from July 17th 2000 to July 31th 2003). The Dutch MoD had no problems with these new dates (decided after meeting).

At this moment the work itself is already delayed about four months, also because of contracting problems. The actual starting date of the work is the date of the kick-off meeting itself. This suggests that the project planning has to be changed (i.e., timeline of work only) and that almost no spare time is left to do the work. The terminology used in the proposal (e.g., adaptable/adaptive) is not always used consistently and this is the second argument for an update of the Technical Proposal (from version 1.1 to version 2.0.). Disregarding earlier remarks the payment schedule remains identical (T0 = new starting date). As more man-hours are spent in 2003 than in the formerly agreed upon schedule and the tariffs for man-hours in 2003 will be higher for all partners. Therefore, in 2003 less hours can be spent (up to 100 hrs in total) than originally planned.

All partners are capable of allocating the required human resource for each year even though the planning has changed.

ACTION BOHNEN: UPDATE TECHNICAL PROPOSAL

Due to the problems with contracting/communication the NLR-budget for project co-ordination in the first year of the project is nearly exhausted.

Responsibilities (see attachments)

Project co-ordinator : Bohnen

SW  co-ordinator : Van Westrenen

Workpackage leaders: (WP 2 to 7: see attachment)

Progress reports

- As agreed upon every 2 months for each WP a progress report will be sent to the project co- ordinator.

ACE concept

See attachment for concept and statements.

Remarks made:

- The ultimate goal of ACE is to support the pilot, either with the cockpit-interface (i.e., information presentation) or with the performance of his/her actions. The logic module (see attachment for complete scheme) will consist of (intelligent) agents. These agents will process the information from the reference module and the input module and will perform intelligent actions on this information. The agents will also determine whether the pilot needs help (i.e. automation to be adaptive), what the help will be and will activate the output module.

- Bravo pilots are the benchmark for the system and should serve as subject’s pilots.  An F-16 simulator at NLR is the testbed The role of the pilot is most successful for the success of the concept.

- Next to the adaptive automation concept itself with the reference, input, logic and output theme’s the model and the architecture of the system should be described in detail.

ACTION BOHNEN: FACILITATE DISCUSSION ON ACE  MODEL AND ARCHITECTURE

Progress of work & group discussions

- The literature review already started and will be finished at the end of June. The partners asked for a few copies of the most relevant literature.

ACTION HANSON: SEND PARTNERS A FEW COPIES OF THE MOST RELEVANT LITERATURE

- In separate groups, discussions about the reference and input theme were held.

- It was remarked that the literature study is meant to give a more conceptual review on adaptive automation as such. Special attention will be paid to examples of existing adaptive automation systems or approaches and how fighter pilots handle (adaptive) automation. The literature review together with user requirements derived from (former) fighter pilots will be used to determine adaptive automation cockpit applications. As those requirements are the most important driving factor for the experiments and the final demonstration and the aim is not to develop SW but to determine whether adaptive automation is useful to pilots.

How to develop each theme will not be addressed in the literature review but is the starting point for the work on each theme in separate WP’s.

- All agreed upon the fact that the development of the total concept can only be successful in case all partners communicate frequently on how they work on each theme. At first it is most essential to have to the total model  available. Parallel development of the reference and input theme is foreseen as both MA and NLR work on both themes. It proves to be difficult or even impossible to discuss on how to do one theme without considering the other.

- Partners requested NLR to provide information about military operations and the role of the pilot therein.

ACTION BOHNEN: TO PROVIDE PARTNERS WITH INFORMATION ABOUT MILITARY OPERATIONS TOGETHER WITH A FRAMEWORK TO DESCRIBE THOSE OPERATIONS

Others

- All deliverables were discussed.

- A discussion unfolded on what adaptivity actually is and how to handle it within ACE. The idea is that it is a point on the continuum of automation and as decided this will be addressed in detail in the literature review.

- The models to be built will be quantitative of nature where should be remarked that qualitative models should not be excluded.

- As remarked by one of the AF representatives’ pilots should feel comfortable when flying with the system. In fact ‘comfort’ is an important design variable.

Next meeting at NLR will be held in the week of June 18th, probably on Thursday and Friday. Only NLR and MA will participate. The topic of the meeting will be WP 3, 4 and 5 together with their relation to other WP’s